## Jan
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection (MI)

## Feb
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## Mar
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## April
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion
C7ACA |  | 2 | CRUZA | Squwak Not Signed off | 2025-04-15 | Returned Work Order Folder to tech for Signed off | Clerical Error (CE)
C8PCA |  | 1 | Hannas/Smikz | Part number in Corrective action and Logbook does not match 8130 | 2025-04-23 | Returned Work Order Folder to tech for part number correction. | Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## May
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
C9BEA |  | 1 | Macos | Model Number of Part installed listed in corrective action and logbook does not match 8130-3 | 2025-05-05 | Notifed Tech of Discrepency Provided copy of GIP-5001 for section 21.12 for issueing an ammended logbook. Requested correction be made and work order to be turned back into QA. | Clerical Error (CE)
CA32A |  | 1 and 2 | Curza/Huber | Aircraft is 135. RTS is 91 | 2025-05-15 | Notifed Tech of Discrepency, Tech to Ammend logbook and work order and resubbmit. | Missing/Incorrect Information (MS)
CA6TA |  | 1 | Curza/Huber | Need more clartifcation on why the maintence is being performed. State we installed a FMS with a teardown report. No reason Why | 2025-05-15 | Notifed Tech of Discrepency, Tech to add additional information to work order and resubbmit. | RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## June
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
CCJDA | MS | 1 | HMICH | Listed AMM Section 34-18-01 used in write up turned in 34-18-00. Airspeed chart not completed | 2025-06-12 | Sent wor kroder back to Tech for clarification | Clerical Error (CE)
CCAAA | MS | 1 | CRUZA | 91.411 and RVSM Charts not completed | 2025-06-12 | Sent Work Order back to tech to complete paperwork | Missing/Incorrect Information (MS)
CAZFA | MS | 2,3,4,6, and Logbook | MACOS | SQ 2,3,4 and Logbook do not state Same form fit and function statement, also SQ 3,4 lists a different title for the servo installed as removed. 91.411 Chart Not Completed or signed. | 2025-06-18 | Sent Work Order back to tech to complete paperwork | RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## July
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## Aug
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## Sept
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
Clerical Error (CE)
Missing/Incorrect Information (MS)
RTS Incorrect/RTS Paperwork Missing (RTS)
Incorrect Work Order Used (IW)
Work Auth not signed (WA)
Missing Inspection

## Oct
Work Order | Org Code | Squwak #/Logbook | Tech | Discrepency | Date | Resaluotion | Dates:
CLHJA | WA | 1 | Ken | Missing Signed Work Agreement | 2026-10-15 | Tech contacted customer and got Agreement signed and resubmit to QA | Clerical Error (CE)
CNKYA | PP | 1 | Ken/John /Jose | Mssing Airport Location and and Work Away block checked in 145 section of work order. | 2025-10-21 | Notified Techs of issue and added Work Away items in block 145. | Missing/Incorrect Information (MS)
CNKYA | RTS | Logbook | Jose | RVSM Logbook not finaled and signed. | 2025-10-21 | Notified Tech about consistency and conformity of paperwork. Tech Signed off Loggbook. | RTS Incorrect/RTS Paperwork Missing (RTS)
CL18A | PP | 1 | Ken/Hannas | Mssing Airport Location and and Work Away block checked in 145 section of work order. | 2025-10-23 | Notified Techs of issue and added Work Away items in block 145. | Incorrect Work Order Used (IW)
DQ4XA | PP | 1 | Ken | Mssing Airport Location and and Work Away block checked in 145 section of work order. | 2025-10-27 | Notified Techs of issue and added Work Away items in block 145. | Work Auth not signed (WA)
CPDAA | RTS | 1 | Sean | Squwak 1 Final Inspection not signed off | 2025-10-27 | Requested Tech to review work order and sign off Squwak final inspection and turn back into QA | Missing Inspection
CMYYA | MS | 1 | John/Jose | Incorrect data listed for Air Data System Checks listed a 34-17-01 instead a 34-17-00. Baro chart in AMM not filled out. Ducnan 91.411 chart not signed. | 2025-10-28 | Notified Techs of issues to have them corrected, and Work Order turned back into QA
CMYYA | MS | Logbook | Ken | Logbook has incorect Ref data listed. Work was performed on 10-22 and and 10/27 logbook is dated for 10/28. Two Logbooks should have been created for the two dates. | 2025-10-28 | Notified Tech about consistency and conformity of paperwork. Issued Amended Logbook
CDG5A | WA | 1 | Ken/Huber/Armando | Missing Signed Work Agreement | 2025-10-29 | Notified Techs. Techs will get Agreement Signed and resubmit to QA
CKTCA | RTS | Logbook | Hannas | Completed Corrective action and Logbook as a 135 operatior. Aircraft is a Part 91. | 2005-10-31 | Notified Lead about consistency and conformity of paperwork. Issued Amended Logbook
CPBSA | MS | Logbook | Ken | Work Performed on 10/29 however logbook is dated for 10/24 | 2025-10-21 | Notified Tech about consistency and conformity of paperwork. Issued Amended Logbook with corrected date.

## Nov
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Dates:
CPTUA | RTS | 1 | CRUZA | Listed unit as Inspected when it should sate Repaired on 8130-3. | 11/7/202 | Discused with Tech and issued and ammended 8130-3 IAW FAA documentation. | Clerical Error (CE)
CQ90A | MI | 1 | NORIJ | Preliminary Inspection not signed off after work was completed on the aicraft | 2025-11-11 | Notifed Tech and requested Prelim Sign off. | Missing/Incorrect Information (MS)
CQ90A | MS | 1 | NORIJ | Tech grabbed alternate part number for back shell that was order for diffreent install and did not verify what part was sold to current install. | 2025-11-11 | Disscussed with Tech about verfiing that parts sold and parts installed match. | RTS Incorrect/RTS Paperwork Missing (RTS)
CQU7A | MS | 1 | MACOS | Work Order missing Special Programs i.e. Part 91, Part 135 Etc.. | 2025-11-17 | Verifed Operating Program and added to CRM notifed tech of findings and corrected Work order | Incorrect Work Order Used (IW)
CP69A | MS | 1 | SMIKZ | Stand-by Altmeter serial number tested did not match the number on the 8130 for the part. | 2025-11-18 | Spoke with tech about slowing down and verifying that write-ups are acurate | Work Auth not signed (WA)
CP69A | MS | 2 | Huber | Stand-by Altmeter serial number installed did not match the number on the 8130 for the part. | 2025-11-18 | Spoke with tech about slowing down and verifying that write-ups are acurate | Missing Inspection (MI)
CP69A | MS | Logobok | SMIKZ | Stand-by Altmeter serial number installed and tested did not match the number on the 8130 for the part. | 2025-11-18 | Spoke with tech about slowing down and verifying that Logbooks are acurate
CP69A | WA | 1 | SMIKZ/HUBER/CRUZA | Final NQ not Signed at time of QA Review | 2025-11-18 | Spoke with all techs involve about making sure there is a signed NQ for work to be perfomed.
CQHTA | MI | 1 | CRUZA | Corrective ation completed and time sold without the Preliminary being signed | 2025-11-13 | Spoke with tech about the importance of signing off in spection at the proper time and requested the prelim be signed off.

## Dec
Work Order | Org Code | Squwak # | Tech | Discrepency | Date | Resaluotion | Month December
CPSQA | MS | 1 | SMIKZ | Listed installed part as Repaired. 8130 state the part was modified. | 2025-12-01 | Sopke with tech about listing the correct status of a part and had tech correct paperwork | Clerical Error (CE)
CRXKA | MS | Sq 1 and Logbook | SMIKZ | Part 135 statement was missing from the corrective action and logbook | 2025-12-03 | Spoke with tech to add the 135 statement to the corrective actiojn and to amednthe logbook as well. | Missing/Incorrect Information (MS)
CQZUA | WA | 1 | CRUZA | Final NQ not Signed at time of QA Review | 2025-12-04 | Spoke tech about making sure there is a signed NQ for work to be perfomed. | RTS Incorrect/RTS Paperwork Missing (RTS)
CQZUA | MS | Sq 3 and Lobook | CRUZA | Missing AD Statement on SQ 3 and Logbook. | 2025-12-04 | Verifed with Tech that AD Reseasch was completed and spoke with them about listing it in the Corrective Action and Logbook. | Incorrect Work Order Used (IW)
CQZUA | RTS | Logbook | HUBER | No Logbook issued for removal of part sent in for repair on Sq 1. | 2025-12-04 | Spoke with tech about documenting maintenace and procedure for RTS. | Work Auth not signed (WA)
DSYQA | RTS | Part 145 | SMIKZ | Part 145 Block with Airprt location and Work Away was not completed. | 2025-12-15 | Notified Tech Tech that the part 145 block needs to be completed to allow for proper RTS sigh off. | Missing Inspection