## Matt Nelson Dec 2025
N# | WO# | Job# | STS | Hdr Dept | Cust # | Customer Name | Manager | Work Description | WMPRTP | Depart Date | WO PM | TL Contact | CAR | Open Date | Days Open | In Date | Prm Date | Cost as of December | Last Labor Sold Date | Days since last labor sold | Last Hrs sold | Deposit (*will appear on all job lines) | Cost as of November
N52584 | 907XA |  | O | SAU | 115903 | TEXAS DEPT OF TRANSPORTATION * | Matt Nelson | PERFORM FAR 91.411 91.413 | C |  | R Rutley | R Rutley |  | 2022-06-14 | 1289 | 2022-06-14 |  | 324.09 | 2022-06-16 | 1287 | 2 | 0 | 324.09
N15TT | 9HYBB | 9HYB | O | SDI | 109214 | J CLEO THOMPSON & * | Matt Nelson | Install X3 & RTS | C |  | S Ward | S Ward |  | 2023-04-25 | 974 | 2023-02-21 |  | -4625 |  |  |  | 0 | -4625
N30VP | K4WJA | K4WJ | O | SHN | 118449 | Aerolineas Ejecutivas | Matt Nelson | DIGITAL FDR LAUNCH STC | C |  | S Carraher | M Winter |  | 2023-12-12 | 743 | 2025-01-06 | 2025-03-31 | 331825.77 | 2025-09-17 | 98 | 8 | 0 | 421825.77
N30VP | K4WJA | K4WJ | O | SHN | 118449 | Aerolineas Ejecutivas | Matt Nelson | DIGITAL FDR LAUNCH STC | C |  | M Winter | M Winter |  | 2023-12-12 | 743 | 2025-01-06 | 2025-03-31 | 331825.77 | 2025-09-17 | 98 | 8 | 0 | 421825.77
N5200 | KFNUA |  | O | SFL | 111842 | Morse Operations Inc * | Matt Nelson | HUD | C |  | B Redondo | B Redondo |  | 2024-04-29 | 604 | 2024-04-29 |  | 116.55 | 2024-05-14 | 589 | 1 | 0 | 116.55
N247JL | KQAMB | KQAM | O | SOA | 148634 | Lynk Air * | Matt Nelson | INDUCED DAMAGE FEE | N |  | A Chavez | A Chavez |  | 2024-10-03 | 447 | 2024-08-16 |  | 2184.33 |  |  |  | 0 | 2184.33
N247JL | KQAMB | KQAM | O | SOA | 148634 | Lynk Air * | Matt Nelson | INDUCED DAMAGE FEE | N |  | A Chavez | J Almeida |  | 2024-10-03 | 447 | 2024-08-16 |  | 2184.33 |  |  |  | 0 | 2184.33
N247JL | KQAMB | KQAM | O | SOA | 148634 | Lynk Air * | Matt Nelson | INDUCED DAMAGE FEE | N |  | J Almeida | J Almeida |  | 2024-10-03 | 447 | 2024-08-16 |  | 2184.33 |  |  |  | 0 | 2184.33
N247JL | KQAMB | KQAM | O | SOA | 148634 | Lynk Air * | Matt Nelson | INDUCED DAMAGE FEE | N |  | J Almeida | A Chavez |  | 2024-10-03 | 447 | 2024-08-16 |  | 2184.33 |  |  |  | 0 | 2184.33
N515LT | KU21A |  | N | SHO | 153627 | 1588 Aviation, LLC * | Matt Nelson | CDU-6000 UNIT RENTAL UNIT | C |  | M Winter | M Winter |  | 2024-10-03 | 447 | 2024-10-03 |  | 15304.44 | 2024-10-05 | 445 | 1 | 0 | 15304.44
| D2FKA | D2FK | O | SFL | 155609 | AVN Parts Inc * | Matt Nelson | BRAKE ASSEMBLY | N |  | B Redondo | B Redondo |  | 2024-10-14 | 436 | 2024-10-14 | 2024-10-24 | 0 |  |  |  | 0 | 0
N551QS | D54VA |  | O | SKI | 106320 | Netjets Aviation Inc. - Maint | Matt Nelson | Gogo L5 w/ MB13 Antennas | A |  |  |  |  | 2024-12-03 | 386 | 2025-12-08 | 2025-12-22 | 140110.62 | 2025-12-04 | 20 | 8 | 0 | 0
N17726 | KYF7A |  | N | SPI | 133837 | Air Commander LLC N17726 | Matt Nelson | Autopilot | C |  | T Lieser | T Lieser |  | 2024-12-04 | 385 | 2024-12-04 |  | 57421.18 | 2025-10-03 | 82 | 1 | 0 | 55692.08
N509QS | D5EDA |  | O | SHN | 106320 | Netjets Aviation Inc. - Maint | Matt Nelson | Gogo L5 w/ MB13 Antennas | A |  | C Sweppenhiser | R Gallehugh |  | 2024-12-06 | 383 | 2025-12-01 | 2025-12-14 | 136483.28 | 2025-11-30 | 24 | 4 | 0 | 0
N822VP | D8MPA |  | O | SVN | 147366 | Planet Nine Private Air LLC | Matt Nelson | Repair KRFU | N |  | P Samaroo | P Samaroo |  | 2025-01-30 | 328 | 2025-01-30 |  | 0 |  |  |  | 0 | 0
N560TV | C3SSA | C3SS | O | SSP | 111622 | Minnesota Jet Inc. | Matt Nelson | Add FMS #2 | C |  | T Lieser | T Lieser |  | 2025-02-13 | 314 | 2025-02-13 |  | 12121.82 | 2025-11-14 | 40 | 0.5 | 0 | 12121.82
| C3ZAA |  | O | SKC | 118484 | Yingling Aircraft Inc. (C) | Matt Nelson | Pack Valve INOP | C |  | J Thuman | J Thuman |  | 2025-02-17 | 310 | 2025-02-17 | 2025-03-31 | 200.89 |  |  |  | 0 | 0
N950JB | C4NUA |  | O | SDA | 132488 | Metroplex Aircraft Inspections | Matt Nelson | EASY II CERT 4 SW UPDATE | C |  | S Ward | S Ward |  | 2025-02-25 | 302 | 2025-02-25 |  | 0 |  |  |  | 0 | 0
N801HH | DB1UA |  | O | STI | 149946 | Hogs Head Air 1 LLC * | Matt Nelson | Star Link install | A | 2025-12-19 | J Glanville | J Glanville |  | 2025-03-12 | 287 | 2025-11-18 | 2025-12-19 | 10054.09 | 2025-12-19 | 5 | 1 | 88206.5 | 0
N436C | C6VSA |  | O | SSP | 117220 | United Healthcare Corp | Matt Nelson | Capacity check | C |  | T Lieser | T Lieser |  | 2025-03-24 | 275 | 2025-03-24 |  | 469.2 | 2025-04-16 | 252 | 5 | 0 | 469.2
N560AW | C8W9A | C8W9 | O | SSP | 111622 | Minnesota Jet Inc. | Matt Nelson | FMS | C |  | T Lieser | T Lieser |  | 2025-04-17 | 251 | 2025-04-17 |  | 245.18 | 2025-12-03 | 21 | 2.5 | 0 | 117.3
N6378M | C8WFA |  | O | SSE | 157103 | Jonathan Flowers * | Matt Nelson | Installation Round 2 | C |  | A Jensen | A Jensen |  | 2025-04-17 | 251 | 2025-04-17 |  | 15994.06 | 2025-12-04 | 20 | 4 | 0 | 8662.5
N714F | CAK0A |  | O | SSP | 151010 | Frauenshuh Inc * | Matt Nelson | Radar SB | C |  | T Lieser | T Lieser |  | 2025-05-09 | 229 | 2025-05-09 |  | 0 |  |  |  | 0 | 0
| DFSVA |  | O | SSE | 135566 | Aero Controls Inc Washington | Matt Nelson | Spares order EX-288922 | N |  | A Jensen | A Jensen |  | 2025-05-29 | 209 | 2025-05-29 |  | 713.37 |  |  |  | 0 | 713.37
N450PC | DFPJA |  | O | SDI | 108933 | DUNCAN AVIONICS-DALLAS 893 | Matt Nelson | ARCHANGEL PC-12 SURVEY | N |  | S Ward | S Ward |  | 2025-05-29 | 209 | 2025-05-29 |  | 2216.18 | 2025-11-18 | 36 | 0.5 | 0 | 2216.18
N23FM | CD40A |  | N | SFL | 157884 | Viper Aviation LLC * | Matt Nelson | SATCOM | C |  | B Redondo | B Redondo |  | 2025-06-13 | 194 | 2025-06-13 |  | 760.5 | 2025-07-11 | 166 | 5 | 0 | 760.5
N687HA | CD3YA |  | N | SDA | 157548 | Cardinal Investment Company * | Matt Nelson | EVS Fails | C |  | S Ward | S Ward |  | 2025-06-13 | 194 | 2025-06-13 |  | 1151.38 | 2025-11-07 | 47 | 0.5 | 0 | 1151.38
N71VT | CE8CA |  | N | SOA | 133876 | Western Wings Corporation | Matt Nelson | Garmin GTN275 Sync | C |  | A Chavez | A Chavez |  | 2025-06-27 | 180 | 2025-06-27 |  | 2946.07 | 2025-11-17 | 37 | 2 | 0 | 2946.07
N1163M | CEXFA | CEXF | O | SNT | 157056 | GRD Aviation LLC * | Matt Nelson | RADAR WON'T PAINT | C |  | G Ashpaugh | G Ashpaugh |  | 2025-07-08 | 169 | 2025-07-08 |  | 2704.29 | 2025-12-03 | 21 | 3 | 0 | 2566.02
N622LM | CG41A |  | O | SDI | 107033 | PepsiCo Inc | Matt Nelson | EDG-100 INSTALL | C |  | S Ward | S Ward |  | 2025-07-23 | 154 | 2025-07-23 |  | 15060.45 | 2025-12-24 | 0 | 8 | 0 | 12103.17
N644KM | CG43A |  | N | SDI | 107033 | PepsiCo Inc | Matt Nelson | EDG-100 INSTALL | C |  | S Ward | S Ward |  | 2025-07-23 | 154 | 2025-07-23 |  | 17569.49 | 2025-12-19 | 5 | 23 | 0 | 11832.99
N628EK | CG4NA | CG4N | F | SDN | 133020 | Kauffman Land & Developmnt LLC | Matt Nelson | FMS WAAS Failures | C |  | E Pita | E Pita |  | 2025-07-23 | 154 | 2025-07-23 | 2025-07-24 | 2485.72 | 2025-10-14 | 71 | 1.5 | 0 | 2485.72
N719NK | DJWCA |  | F | SAC | 142808 | Pacific Coast Jet LLC | Matt Nelson | FLIGHT MANAGEMENT | N |  | G Gancarz | G Gancarz |  | 2025-07-24 | 153 | 2025-07-24 |  | 0 |  |  |  | 0 | 0
N301RD | CGERA |  | O | SSP | 133998 | Life Time Inc. | Matt Nelson | TCAS Fails Above 900 FT | C |  | T Lieser | T Lieser |  | 2025-07-28 | 149 | 2025-07-28 |  | 6752.87 | 2025-12-15 | 9 | 4.5 | 0 | 6522.7
N319ST | DK5NA |  | O | SAC | 146816 | 30 West Jets * | Matt Nelson | WARRANTY EXCHANGE | N |  | G Gancarz | G Gancarz |  | 2025-07-28 | 149 | 2025-07-28 |  | 0 |  |  |  | 0 | 0
N917SM | DKFFA | DKFF | F | SFL | 148223 | Sky Jets Management Support * | Matt Nelson | EFD #3 | N |  | B Redondo | B Redondo |  | 2025-07-31 | 146 | 2025-07-31 |  | 0 |  |  |  | 0 | 0
N713ST | DKSGA | DKSG | O | SFW | 147097 | JDM Aviation Services LLC | Matt Nelson | STANDBY ATTITUDE IND FAIL | N |  | S Ward | T Miallie |  | 2025-08-05 | 141 | 2025-08-05 |  | 60.67 | 2025-08-05 | 141 | 1 | 0 | 60.67
| DKVCA |  | C | SDN | 132595 | Sierra Nevada Corp | Matt Nelson | Ovhl 1 Oxygen Mask | N |  | E Pita | E Pita |  | 2025-08-06 | 140 | 2025-08-06 |  | 2051.52 | 2025-12-22 | 2 | 1 | 0 | 93.12
| DLBTA |  | O | SDN | 108928 | DUNCAN AVIONICS-DENVER 889 | Matt Nelson | EDG-100 Kit & Antenna | N |  | E Pita | E Pita |  | 2025-08-18 | 128 | 2025-08-18 |  | 0 |  |  |  | 0 | 0
N319ST | DLH4A |  | O | SAC | 146816 | 30 West Jets * | Matt Nelson | TCAS | N |  | G Gancarz | G Gancarz |  | 2025-08-20 | 126 | 2025-08-20 |  | 0 |  |  |  | 0 | 0
| DLKKA |  | O | SSE | 135566 | Aero Controls Inc Washington | Matt Nelson | Spares order EX-293340 | N |  | A Jensen | A Jensen |  | 2025-08-21 | 125 | 2025-08-21 |  | 0 |  |  |  | 0 | 0
N171AM | CK7BA |  | N | SFL | 130390 | Florida Jet Center | Matt Nelson | #1 Comm has static noise | C |  | B Redondo | B Redondo |  | 2025-09-02 | 113 | 2025-09-02 |  | -153.35 | 2025-11-07 | 47 | 8 | 0 | 6573.07
N569TA | CKCQA |  | O | SFW | 158438 | Cowtown Flight Management | Matt Nelson | TROUBLESHOOT RADIOS CUT O | C |  | C Bocanegra | T Miallie |  | 2025-09-03 | 112 | 2025-09-03 | 2025-09-04 | 0 |  |  |  | 0 | 0
N569TA | CKCQA |  | O | SFW | 158438 | Cowtown Flight Management | Matt Nelson | TROUBLESHOOT RADIOS CUT O | C |  | S Ward | T Miallie |  | 2025-09-03 | 112 | 2025-09-03 | 2025-09-04 | 0 |  |  |  | 0 | 0
N996GA | CKG3A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Roque | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N996GA | CKG3A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Marte | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N996GA | CKG4A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Roque | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N996GA | CKG4A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Marte | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N996GA | CKG5A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Marte | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N996GA | CKG5A |  | O | SWP | 142789 | Journey Aviation | Matt Nelson | Avionics Support | C |  | P Roque | P Marte |  | 2025-09-04 | 111 | 2025-09-04 | 2025-09-05 | 0 |  |  |  | 0 | 0
N196X | CKKVA |  | N | SFW | 147097 | JDM Aviation Services LLC | Matt Nelson | QFEEL DOWNLOAD | C |  | S Ward | T Miallie |  | 2025-09-05 | 110 | 2025-09-05 |  | 794.54 | 2025-10-27 | 58 | 1 | 0 | 786.14
N805AL | DMJKA | DMJK | O | SWP | 144321 | New England Business Aviation | Matt Nelson | RADIO ALTIMETER RT-300 | N |  | P Marte | P Marte |  | 2025-09-08 | 107 | 2025-09-08 | 2025-09-18 | 0 |  |  |  | 0 | 0
N615FJ | DMJ5A |  | C | SFW | 157352 | Trifecta Aviation LLC * | Matt Nelson | PITOT/STATIC LEAK CHECK | U |  | S Ward | T Miallie |  | 2025-09-08 | 107 | 2025-09-08 |  | 489.54 | 2025-12-15 | 9 | 0.5 | 0 | 466.7
N430DD | CKU6A |  | C | SFW | 146739 | Sav Aviation LLC * | Matt Nelson | TROUBLESHOOT AP ISSUES | C |  | C Bocanegra | T Miallie |  | 2025-09-09 | 106 | 2025-09-10 | 2025-09-11 | 428.27 | 2025-12-16 | 8 | 0.5 | 0 | 592.11
N430DD | CKU6A |  | C | SFW | 146739 | Sav Aviation LLC * | Matt Nelson | TROUBLESHOOT AP ISSUES | C |  | S Ward | T Miallie |  | 2025-09-09 | 106 | 2025-09-10 | 2025-09-11 | 428.27 | 2025-12-16 | 8 | 0.5 | 0 | 592.11
N428MG | CKU8A |  | C | SFW | 146739 | Sav Aviation LLC * | Matt Nelson | PERFORM FAR 91.411 & 413 | C |  | C Bocanegra | T Miallie |  | 2025-09-09 | 106 | 2025-09-10 | 2025-09-11 | 1049.98 | 2025-12-16 | 8 | 2.5 | 0 | 749.12
N428MG | CKU8A |  | C | SFW | 146739 | Sav Aviation LLC * | Matt Nelson | PERFORM FAR 91.411 & 413 | C |  | S Ward | T Miallie |  | 2025-09-09 | 106 | 2025-09-10 | 2025-09-11 | 1049.98 | 2025-12-16 | 8 | 2.5 | 0 | 749.12
N967BG | CKU3A |  | N | SWP | 157965 | Sunset Aviation LLC (N967BG) | Matt Nelson | ATG 5000 | C |  | P Marte | P Marte |  | 2025-09-09 | 106 | 2025-09-09 |  | 132.79 | 2025-09-30 | 85 | 1 | 0 | 132.79
N926PN | DMN6A |  | O | SVN | 147366 | Planet Nine Private Air LLC | Matt Nelson | MHC-II Controller | N |  | P Samaroo | P Samaroo |  | 2025-09-09 | 106 | 2025-09-09 |  | 0 |  |  |  | 0 | 0
N787NB | DMPSA |  | O | STB | 151974 | Superior Jet Maintenance * | Matt Nelson | AUDIO/VIDEO MODULE | N |  | L Bozetarnik | L Bozetarnik |  | 2025-09-10 | 105 | 2025-09-10 |  | 36214.2 |  |  |  | 0 | 36214.2
N214AH | DMXLA |  | C | SFW | 127079 | Guardian Flight LLC | Matt Nelson | ASSIST W/TEST SET ALT8000 | U |  | S Ward | T Miallie |  | 2025-09-16 | 99 | 2025-09-16 |  | 588.49 | 2025-12-16 | 8 | 0.5 | 0 | 565.65
| CLF0A |  | O | SKC | 142483 | Canadian Pacific Railway | Matt Nelson | Overhaul NiCad | C |  | J Thuman | J Thuman |  | 2025-09-16 | 99 | 2025-09-16 | 2025-10-31 | 587.89 | 2025-10-03 | 82 | 10.1 | 0 | 587.89
N3LL | CLHQA |  | N | SFL | 154280 | Elite Jet Services LLC * | Matt Nelson | EVS | C |  | B Redondo | B Redondo |  | 2025-09-17 | 98 | 2025-09-17 |  | 414.4 | 2025-09-18 | 97 | 8 | 1539.2 | 414.4
N931DC | CLGDA |  | N | SLN | 157028 | Quarry Capital * | Matt Nelson | C1 UPGRADE | C |  | J Robbins | J Robbins |  | 2025-09-17 | 98 | 2025-09-17 |  | 20108.79 | 2025-11-25 | 29 | 18.2 | 0 | 17596.44
N303JJ | DN1KA | DN1K | O | SDN | 109004 | International Jet Aviation (C) | Matt Nelson | OVHL Starter Generator | N |  | E Pita | E Pita |  | 2025-09-18 | 97 | 2025-09-18 | 2025-09-19 | 47.38 | 2025-09-18 | 97 | 1 | 0 | 47.38
N3712C | CLQZA | CLQZ | O | SSP | 136381 | Aircraft Maintenance | Matt Nelson | KAC-952S TO LNK | C |  | T Lieser | T Lieser |  | 2025-09-19 | 96 | 2025-09-19 |  | 172.3 |  |  |  | 0 | 0
N519PC | DN3GA |  | F | SDN | 132595 | Sierra Nevada Corp | Matt Nelson | Repair Temp Control Valve | N |  | E Pita | E Pita |  | 2025-09-19 | 96 | 2025-09-19 |  | 45503.34 | 2025-12-22 | 2 | 0.5 | 0 | 47.38
N319ST | DN8EA |  | O | SVN | 146816 | 30 West Jets * | Matt Nelson | Warranty repair DDU | N |  | P Samaroo | P Samaroo |  | 2025-09-23 | 92 | 2025-09-23 |  | 0 |  |  |  | 0 | 0
N856T | CM20A | CM20 | O | SSP | 146127 | Just-In-Time A/C Contracting * | Matt Nelson | MFD Blanks Out | C |  | T Lieser | T Lieser |  | 2025-09-24 | 91 | 2025-09-24 |  | 3881.83 |  |  |  | 0 | 0
N23FM | CLZ7A |  | O | SFL | 143426 | SA AIRCRAFT SERVICES * | Matt Nelson | CABIN AIR TOO COLD | C |  | B Redondo | B Redondo |  | 2025-09-24 | 91 | 2025-09-24 |  | 0 |  |  |  | 0 | 0
N319ST | DNPQA |  | O | SAC | 146816 | 30 West Jets * | Matt Nelson | MPP EXCHANGE UNITS | N |  | G Gancarz | G Gancarz |  | 2025-09-25 | 90 | 2025-09-25 |  | 47.9 |  |  |  | 0 | 0
N2MK | CM5UA |  | O | SFL | 108875 | Intercontinental Jet Serv Corp | Matt Nelson | Check Radar | C |  | B Redondo | B Redondo |  | 2025-09-26 | 89 | 2025-09-26 |  | 196.64 | 2025-09-26 | 89 | 4 | 0 | 0
N569CG | CM5ZA |  | O | SPI | 111622 | Minnesota Jet Inc. | Matt Nelson | L5 | C |  | T Lieser | T Lieser |  | 2025-09-26 | 89 | 2025-09-26 |  | 151223.69 | 2025-11-14 | 40 | 8 | 0 | 0
| DNQXA |  | O | SDN | 132595 | Sierra Nevada Corp | Matt Nelson | Repair Temp Control Valve | N |  | E Pita | E Pita |  | 2025-09-26 | 89 | 2025-09-26 |  | 96.66 | 2025-10-03 | 82 | 1 | 0 | 0
N453JG | CM5LA |  | O | SDA | 112453 | North Texas Aircraft Services | Matt Nelson | MAG 1 failure | C |  | S Ward | S Ward |  | 2025-09-26 | 89 | 2025-09-26 |  | 6087.77 | 2025-12-02 | 22 | 1 | 0 | 0
N23ZT | CM5QA |  | O | SFL | 143426 | SA AIRCRAFT SERVICES * | Matt Nelson | UPDATE DATABASES | C |  | B Redondo | B Redondo |  | 2025-09-26 | 89 | 2025-09-26 |  | 196.64 | 2025-09-25 | 90 | 4 | 0 | 0
N8341C | CMB1A |  | O | SPI | 133837 | Air Commander LLC N17726 | Matt Nelson | Intall USB Port | C |  | T Lieser | T Lieser |  | 2025-09-29 | 86 | 2025-09-29 |  | 1111.1 | 2025-10-31 | 54 | 7 | 0 | 0
N650KP | CMCLA |  | N | SAC | 151908 | AeroSim Inc * | Matt Nelson | GO AROUND INOP | C |  | G Gancarz | G Gancarz |  | 2025-09-29 | 86 | 2025-09-29 |  | 282 | 2025-09-29 | 86 | 6 | 0 | 0
N732RJ | DNTGA | DNTG | O | SFL | 156094 | Mustfly LLC * | Matt Nelson | LEAR 60 STR/GEN | N |  | B Redondo | B Redondo |  | 2025-09-29 | 86 | 2025-09-29 | 2025-10-28 | 7.11 | 2025-10-03 | 82 | 0.2 | 0 | 0
N326N | DNURA |  | T | SFL | 131150 | Catalina Aerospace Corp | Matt Nelson | Flight Control Computer | N |  |  |  |  | 2025-09-29 | 86 | 2025-09-29 |  | 0 |  |  |  | 0 | 0
XB-JAM | DNXCA |  | O | SDA | 156057 | Servicios Ejecutivos de * | Matt Nelson | Billable exchang KST-488 | N |  | S Ward | S Ward |  | 2025-09-30 | 85 | 2025-09-30 |  | 3208.64 | 2025-10-15 | 70 | 2 | 0 | 0
N3712C | CMEPA |  | O | SPI | 136381 | Aircraft Maintenance | Matt Nelson | CMU Upgrade | C |  | T Lieser |  |  | 2025-09-30 | 85 | 2025-09-30 |  | 119726.26 | 2025-11-13 | 41 | 9 | 0 | 0
N1870E | CMJHA |  | O | SDV | 142915 | Business Aviators Inc | Matt Nelson | Ensemble Upgrade | C |  | E Pita | E Pita |  | 2025-10-01 | 84 | 2025-10-01 |  | 290.48 | 2025-11-07 | 47 | 2 | 0 | 0
N1ES | CMKQA |  | O | SFL | 109330 | Jet Harbor Inc | Matt Nelson | AIR DATA COMPUTER | C |  |  |  |  | 2025-10-02 | 83 | 2025-10-02 | 2025-10-17 | 61.03 |  |  |  | 0 | 0
N21LG | CMLWA | CMLW | O | SFW | 144416 | Swartz Aviation Group LLC * | Matt Nelson | #1 HDG 10 DEGREES OFF | C |  | S Ward | T Miallie |  | 2025-10-02 | 83 | 2025-10-02 |  | 5963.58 | 2025-12-02 | 22 | 0.5 | 0 | 0
N669BB | CMNUA |  | O | SDI | 135277 | Trinity Jet Management * | Matt Nelson | GOGO C1 UPDATE | C |  | S Ward | S Ward |  | 2025-10-02 | 83 | 2025-10-02 |  | 18522.71 | 2025-12-09 | 15 | 0.5 | 0 | 0
N541HC | CMLXA | CMLX | N | SOI | 120135 | Global Aviation Incorporated | Matt Nelson | ELT4000 Upgrade | C |  | J Almeida | J Almeida |  | 2025-10-02 | 83 | 2025-12-18 |  | 22060.32 | 2025-12-18 | 6 | 2 | 0 | 0
N352WB | CMRAA |  | O | SFL | 109330 | Jet Harbor Inc | Matt Nelson | MFD DISPLAY FLOODING | C |  | B Redondo | B Redondo |  | 2025-10-03 | 82 | 2025-10-03 |  | 2597.22 | 2025-10-08 | 77 | 1.5 | 0 | 0
N270PC | C6G3B | C6G3 | O | SGI | 119025 | Southern Company Services | Matt Nelson | GCMS GOGO L5 Interconnect | C |  | E Carrillo | E Carrillo |  | 2025-10-03 | 82 | 2025-03-19 |  | 2181.86 | 2025-10-07 | 78 | 2 | 310511.96 | 0
N254SB | CMXEA |  | O | SFL | 131344 | Execuflight | Matt Nelson | STALL WARN/IDENT CHECK | C |  | B Redondo | B Redondo |  | 2025-10-06 | 79 | 2025-10-06 |  | 694.14 | 2025-11-24 | 30 | 2 | 0 | 0
N713JM | CMXHA |  | O | SFL | 156758 | JP Ashley LLC * | Matt Nelson | #2 HF SYSTEM INOPERATIVE | C |  | B Redondo | B Redondo |  | 2025-10-06 | 79 | 2025-10-06 |  | 197.18 | 2025-10-31 | 54 | 2 | 0 | 0
N319ST | DP8MA |  | O | SAC | 146816 | 30 West Jets * | Matt Nelson | Temp stuck at 80 degrees | N |  | G Gancarz | G Gancarz |  | 2025-10-06 | 79 | 2025-10-06 |  | 0 |  |  |  | 0 | 0
N55423 | CN08A |  | O | STR | 157957 | Prescott Flying Club * | Matt Nelson | Servo | C |  | T Lieser |  |  | 2025-10-07 | 78 | 2025-10-07 |  | 0 |  |  |  | 0 | 0
N232TX | CN15A |  | O | STR | 103880 | Cash Invoices--LNK * | Matt Nelson | 24 Month IFR | C |  |  | V Fogarty |  | 2025-10-07 | 78 | 2025-10-07 |  | 0 |  |  |  | 0 | 0
N598KD | CN3LA |  | F | SAC | 142835 | Wildhorse LLC * | Matt Nelson | SKIN WAV TEST | C |  | G Gancarz | G Gancarz |  | 2025-10-08 | 77 | 2025-10-08 |  | 0 |  |  |  | 0 | 0
N866BB | CN59A |  | O | SFL | 134994 | Best Jets International | Matt Nelson | CVR | C |  | B Redondo | B Redondo |  | 2025-10-09 | 76 | 2025-10-09 |  | 0 |  |  |  | 0 | 0
N3LH | CN75A | CN75 | N | SHO | 144579 | Silverstar Partners LLC | Matt Nelson | T/S APS-80 AUTOPILOT | C |  | C Sweppenhiser |  |  | 2025-10-09 | 76 | 2025-10-09 |  | 0 |  |  |  | 0 | 0
N270PC | C6G3C | C6G3 | O | SGI | 119025 | Southern Company Services | Matt Nelson | GCMS LX5 Systems Integrat | C |  | E Carrillo | E Carrillo |  | 2025-10-09 | 76 | 2025-03-19 |  | 164.97 | 2025-11-18 | 36 | 1 | 310511.96 | 0
N339B | DPHAA |  | O | SAC | 126907 | Concord Jet Service Inc | Matt Nelson | HAPP | N |  | M Rayos del Sol | G Gancarz |  | 2025-10-10 | 75 | 2025-10-10 | 2025-10-11 | 0 |  |  |  | 0 | 0
N339B | DPHAA |  | O | SAC | 126907 | Concord Jet Service Inc | Matt Nelson | HAPP | N |  | G Gancarz | G Gancarz |  | 2025-10-10 | 75 | 2025-10-10 | 2025-10-11 | 0 |  |  |  | 0 | 0
N786CJ | DPKCA |  | O | SFL | 154967 | Crystal Motorsports * | Matt Nelson | VHF-422D Radio | N |  | B Redondo | B Redondo |  | 2025-10-13 | 72 | 2025-10-13 |  | 0 |  |  |  | 0 | 0
N715GC | CNDBA |  | O | SDA | 154977 | 6TS Holdings LLC * | Matt Nelson | Autopilot failure | C |  | S Ward | S Ward |  | 2025-10-13 | 72 | 2025-10-16 | 2025-10-17 | 2376.14 | 2025-11-12 | 42 | 1.5 | 0 | 0
N546DM | CNF7A |  | O | STR | 143350 | Exclusive Aerospace LLC | Matt Nelson | Software Update | C |  | T Lieser | T Lieser |  | 2025-10-14 | 71 | 2025-10-14 |  | 636.38 | 2025-10-15 | 70 | 4 | 0 | 0
N795SP | DPMHA |  | O | SKC | 143976 | Lockton Enterprises | Matt Nelson | MSP RENEWAL | N |  | J Thuman | J Thuman |  | 2025-10-14 | 71 | 2025-10-14 |  | 68.51 | 2025-12-12 | 12 | 1 | 144025.2 | 0
N800PL | CNGKA |  | O | SFL | 155684 | Executive Flight Solution Corp | Matt Nelson | UPDATE EGPWS | C |  | B Redondo | B Redondo |  | 2025-10-14 | 71 | 2025-10-14 |  | 147.48 | 2025-10-13 | 72 | 3 | 0 | 0
N466F | CNMRA |  | O | SAC | 142808 | Pacific Coast Jet LLC | Matt Nelson | ACP-4130 | C |  | G Gancarz | G Gancarz |  | 2025-10-15 | 70 | 2025-10-15 |  | 1674 |  |  |  | 0 | 0
N7799T | CNLRA |  | O | SVN | 147366 | Planet Nine Private Air LLC | Matt Nelson | Reterminate Coax | C |  | P Samaroo | P Samaroo |  | 2025-10-15 | 70 | 2025-10-15 |  | 256 |  |  |  | 0 | 0
N659NR | CL4CB |  | O | SDN | 142915 | Business Aviators Inc | Matt Nelson | Install Radar | C |  | E Pita |  |  | 2025-10-16 | 69 | 2025-09-11 | 2025-10-16 | 0 |  |  |  | 0 | 0
N122PR | CNR1A |  | O | SAC | 137844 | V1 Aviation Inc. * | Matt Nelson | WIFI TEST | C |  | G Gancarz | G Gancarz |  | 2025-10-16 | 69 | 2025-10-16 |  | 965.07 | 2025-11-25 | 29 | 1.5 | 0 | 0
N8341C | CNU5A |  | N | SSP | 133837 | Air Commander LLC N17726 | Matt Nelson | Instrument/Panel lighting | C |  | T Lieser | T Lieser |  | 2025-10-17 | 68 | 2025-10-17 |  | 50.91 | 2025-10-17 | 68 | 1 | 0 | 0
N744N | CNSGA |  | O | SFL | 112313 | Noble Jet Inc. | Matt Nelson | Autopilot ILS Fault | C |  | B Redondo | B Redondo |  | 2025-10-17 | 68 | 2025-10-17 |  | 49.16 | 2025-10-17 | 68 | 1 | 0 | 0
N711MC | DPTLA |  | O | SHN | 110943 | MCA-ATS | Matt Nelson | TRAVEL TO SLN | N |  | C Sweppenhiser | C Sweppenhiser |  | 2025-10-17 | 68 | 2025-10-17 |  | 45127.83 | 2025-11-08 | 46 | 68 | 0 | 0
N567MC | CNXLA |  | C | SVI | 135845 | Mach One Air Charter Inc | Matt Nelson | FMS Upgrade | C |  | P Samaroo | P Samaroo |  | 2025-10-20 | 65 | 2025-10-20 |  | 72313.49 | 2025-12-23 | 1 | 1.4 | 118969.3 | 0
N350RR | CNZ2A |  | O | SFW | 119227 | ProAviation Services Inc | Matt Nelson | REPLACE ELT CONNECTOR | C |  | S Ward | T Miallie |  | 2025-10-20 | 65 | 2025-10-20 |  | 426.79 | 2025-10-23 | 62 | 5 | 0 | 0
N98XS | CP2WA |  | T | SNI | 145577 | Merlin One Aircraft LLC | Matt Nelson | Evaluate NEW INSTALL L3 | C |  |  |  |  | 2025-10-21 | 64 | 2025-10-21 |  | 6791.4 | 2025-12-22 | 2 | 2 | 64700 | 0
N280PC | KW82F | KW82 | O | SGI | 119025 | Southern Company Services | Matt Nelson | GCMS/GOGO Avance Interfac | C |  | E Carrillo | E Carrillo |  | 2025-10-21 | 64 | 2024-11-04 |  | 39.97 | 2025-11-18 | 36 | 1 | 0 | 0
N499PH | CPA2A |  | O | SFL | 109330 | Jet Harbor Inc | Matt Nelson | #1 EHSI HEADING | C |  | B Redondo | B Redondo |  | 2025-10-23 | 62 | 2025-10-23 |  | 98.86 | 2025-10-22 | 63 | 2 | 0 | 0
[7 empty] | Matt Nelson | [10 empty] | 1688760.3 |  |  |  |  | 1050138.23